## excel (2)
Planned Completion Date: | 2016-04-25
Replanned Completion Date: | 2016-02-25
Replanned Cost: | 3.15 | (3.15 hours)
Cost Variance: | -1.15 | (1.15 hours over budget)
Cost Variance %: | -57% | (57% over budget)
Cost Performance Index: | 0.635
Schedule Variance: | 2 | (2 hours ahead of schedule)
Schedule Variance Duration: | 0.376 | (9.03 hours ahead of schedule)
Percent Complete: | 100%
Percent Spent on Completed Tasks: | 158%
To Complete Performance Index: | 0
Improvement Ratio: | -1
Forecast Cost: | 3.15 | (3.15 hours)
Forecast Duration: | 0.376 | (9.03 hours)
Forecast Completion Date: | 2016-02-25
Project/Task | PT | Time | PV | Plan Date | Replan | Forecast | Date | Dep | %C | %S | EV
/Project | 0.083333 | 0.13125 | 100% | 2016-04-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 |  | 100% | 158% | 100%
From | To | PT | CPT | CPV | Time | CT | EV
2016-02-25 | 2016-03-25 | 0.041667 | 0.041667 | 0% | 0 | 0.13125 | 100%
2016-03-25 | 2016-04-25 | 0.041667 | 0.083333 | 100% | 0 | 0.13125 | 100%